## Slide 1
TECH LEADERSHIP · EXECUTION DEEP DIVE
Data Observability Platform
What broke, why, who is affected, how it stops recurring — four foundations, three teams, six months to a live pilot.
Roadmap · Milestones · Outcomes
August 2026
Notes: 45-min deep dive compressed to 10 slides: problem, approach, roadmap, milestones, teams, governance, outcomes.

## Slide 2
THE PROBLEM
Failures live in the seams — one incident, run both ways
Today
≈ 2 days to truth
Day 1 · Job exits 0 — "success" — 8% of rows silently NULLed. No alert.
Day 2 · Analyst notices revenue looks low. Decisions already made.
+4–6 hrs · War room: 4 teams paged, every tool reports green.
On the platform
≈ 30 minutes
+2 min · Monitor spots the NULL spike at the topic — one hop from cause.
+20 min · One incident, cause attached. One team paged, not four.
+30 min · Gate holds the bad batch; consumers stay on last-certified.
~$2M/yr lost per 50 affected engineers
4+ hrs war room per cross-team failure
0 alerts on silent failures today
Notes: One incident, run both ways. Today: batch job exits 0, analyst finds it two days later, four teams paged. Target: detected in 2 minutes, one team paged, gate holds the bad batch. The gap is structural — nobody owns the seams.

## Slide 3
THE APPROACH
Four questions, four foundations
What broke?
↓
Batch + post-write + streaming DQ, federated in one evidence stream
Live M1–M3
Why?
↓
E2E lineage joined to evidence + deploy events — cause on the incident card
Live M4–M5
Who is affected?
↓
Lineage + consumer bindings — blast radius on click
Live M4
How does it stop recurring?
↓
Contracts + certification gate — bad data held, not found
Live M6–M7
By month 18: bad data never reaches a Tier-1 consumer unseen · a new use case onboards in ≤ 2 weeks · every lineage edge carries a confidence score.
Notes: Each leadership question maps to one foundation and has a named moment it first runs on real data. By month 18: no bad data reaches Tier-1 unseen; onboarding ≤ 2 weeks; every edge confidence-scored.

## Slide 4
THE APPROACH
Horizontal foundations, proven vertically
ONE PILOT THREAD — EVERY MILESTONE IS A DEMO ON IT
payments-svc
→
orders topic
→
enrichment job
→
gold.orders_enr
→
finance report
1
Milestones are demos, never a percent-complete.
2
Nothing counts until it lands in the shared evidence stream.
3
Existing batch DQ is federated, never replaced.
Rejected: tool-per-team (more islands) · big-bang platform (18 months dark, no kill switch) · use-case one-offs (nothing compounds).
Notes: Foundations are horizontal — built once, inherited by every use case — but proven vertically on one pilot thread in six months. Rejected: tool-per-team (more islands), big-bang (18 months dark), one-offs (nothing compounds).

## Slide 5
ROADMAP
Three horizons, eight demo milestones
NOW · months 1–6 · the commitment
NEXT · m7–9 · via gate
HORIZON · m10+
M1 m1
Evidence stream + registry live; batch DQ federated
M2 m2
Post-write DQ learns "normal" — auto checks
M3 m3
Streaming DQ live; first silent catch, saves banked
M4 m4–5
Lineage joined; blast radius + cause live
M5 m6
UC1 live end-to-end · go/no-go gate
M6 m7–8
First producer-accepted contract
M7 m8–9
Gate's first real block; zero exposure
M8 m9
UC2 onboarded: 6 weeks → 2
P4 · by trigger
Simulation · in-path asserts · onboarding automation · column-level
Every milestone is a demo on the pilot thread, with an accountable team.
Horizon runs on triggers, not dates — e.g. simulation ← scored graph; automation ← two manual onboardings.
Notes: Three horizons. Now is the commitment, ending at the month-6 gate. Next is entered only through the gate. Horizon capabilities switch on by trigger, not date: simulation needs a scored graph; in-path needs a contract plus a recurring violation; automation needs two manual onboardings.

## Slide 6
ROADMAP
Every pillar climbs one level per phase
L0 doesn't exist
L1 islands
L2 connected
L3 runs itself
L4 prevents
PILLAR
TODAY
MONTH 6 GATE
MONTH 12
MONTH 18
Batch data quality
L1
L2
L3
L4
Post-write DQ (at rest)
L1
L2
L3
L4
Streaming DQ (real-time)
L1
L2
L3
L3+
E2E lineage
L1
L2
L3
L3+
Data contracts
L0
L1
L3
L4
Onboarding + dashboard
L1
L1–L2
L2–L3
L3
No pillar jumps two levels in a phase. L4-everywhere is deliberately not the goal — maturity is matched to asset tier.
Notes: Each pillar climbs one level per phase — no pillar jumps two. L4-everywhere is deliberately not the goal; maturity is matched to asset tier. Contracts start at L0 by design: drafted from observed behavior, not workshops.

## Slide 7
EXECUTION
Three missions of ten, converging on one platform
Lineage & Confidence
10
The platform core: capture → join → score → simulate. Owns the evidence stream and registry.
Data Quality
10
Detection → prevention: checks at rest, in-stream monitoring, then contracts and the gate.
Onboarding & Experience
10
Adoption & the surface: dashboard, paved road, saves ledger, the M5 gate pack.
↓ ↓ ↓
One evidence stream · one pilot thread · one scorecard
Every definition of done lands here — weekly joined demo from week 4 · milestone = cross-team demo · no team runs >3 concurrent builds
Notes: Three missions of ten, each owning one foundation end-to-end — nobody split across projects. Convergence is engineered: shared definition of done, weekly joined demo from week 4, milestone = cross-team demo.

## Slide 8
EXECUTION
Critical path — one decision, three read-only asks
THE CRITICAL ASK · P0
One naming registry as the authority
Data platform / governance. Scoped to the pilot's ~10 assets to be decidable fast — without it, every join fails silently later.
READ-ONLY · P0
Streaming platform
Monitor credentials + topic catalog. Plan B: detect at tables.
READ-ONLY · M1
Central DQ tooling
Check results. Plan B: scheduled export, slightly staler.
READ-ONLY · M4
CI/CD deploy events
Commit + timestamp, pilot only. Plan B: infer from logs.
Cross-team interlocks are dated (weeks 3–4) with versioned stubs as fallback. Dependency health is a monthly scorecard item with sponsor escalation — a slip is surfaced, never absorbed silently.
Notes: One decision-ask: the naming registry as authority, scoped to the pilot's ~10 assets so it's decidable fast — without it every join fails silently later. Everything else is read-only access with a Plan B. Dependency health is on the monthly scorecard with sponsor escalation.

## Slide 9
GOVERNANCE
How leadership keeps control
Saves ledger
Every catch logged with its counterfactual cost. Opens at M1.
Monthly scorecard
Time-to-detect, teams paged, saves banked, dependency health.
Live-replay reviews
Milestones are demos on the pilot thread — no "percent complete."
Sponsor-owned KPI
The pilot maps to one executive sponsor's own metric.
KILL CRITERIA — STATED UP FRONT
No real saves and no time-to-detect improvement by the month-6 gate → the program stops and thirty engineers redeploy. Decided on the scorecard, not on architecture progress.
Notes: Fixed cadence so silence is never read as stall; reviews are live replays, not status decks. And the kill switch: no real saves and no detection improvement by month 6 → the program stops. That offer is what makes the vision credible.

## Slide 10
OUTCOMES
What is live at months 6, 11, and 18
Month 6
Proven
Four foundations live and joined on use case 1 — health, cause, blast radius. Go/no-go gate.
Month 11
Enforcing
Full platform live — gating on, edges confidence-scored, multiple use cases on the paved road.
Month 18
Scaled
Critical use cases operating; impact simulation on Tier-1; onboarding ≤ 2 weeks; expansion priced from measured cost per use case.
Three missions, one evidence stream, one pilot thread, one scorecard — one platform, not three projects.
Notes: The outcome ladder: month 6 proof, month 11 full platform, month 18 scaled and priced. Close on discipline — what we refuse to do is half the vision. One platform, not three projects.