## Slide 1
TECH LEADERSHIP · EXECUTION DEEP DIVE
Data Observability Platform
One platform that answers what broke, why, who is affected, and how it stops recurring — four foundations, three mission teams, six months to a live pilot.
Roadmap · Milestones · Outcomes
August 2026
Notes: Frame the session: this is a status deep dive on execution — problem, strategy, roadmap, milestones, teams, governance, outcomes. 45 minutes.

## Slide 2
AGENDA
Six parts, forty-five minutes
01
The problem
Failures in the seams — one incident, run both ways
02
Target state & strategy
Four questions, four foundations, one pilot thread
03
Roadmap & milestones
Three horizons; every milestone is a demo
04
Teams & capacity
Three missions of ten; convergence engineered
05
Critical path & governance
Dependencies, scorecards, kill criteria
06
Outcomes
What is live at months 6, 11, and 18
Notes: Six parts. Heaviest weight on roadmap and milestones per the ask; governance and outcomes close.

## Slide 3
01 · THE PROBLEM
Failures live in the seams — and nobody owns the seams
A payments service adds a new status value. Every team's own monitoring stays green. Signals exist everywhere, but they are islands that cannot reference each other — no individual tool can close a structural gap.
~$2M/yr
lost capacity per 50 affected engineers from data incidents
4+ hrs
of war room per cross-team failure — four teams paged for one team's change
0 alerts
on silent failures — bad data is found by an analyst, after decisions are made
Notes: The gap is structural, not tooling. Signals exist everywhere but are islands. Nobody owns the seams between systems.

## Slide 4
01 · THE PROBLEM
Incident anatomy — today
≈ 2 days to truth
Day 1
Upstream change silently maps new values to NULL. The batch job exits 0 — "success" — writing 8% fewer valid rows. No alert fires anywhere.
Day 2
A finance analyst notices revenue looks low. Decisions have already been made on the wrong number.
+4–6 hrs
War room: four teams paged, each tool truthfully reports its slice healthy. Root cause found by hand-diffing row counts.
Cost: 4+ hours × 5 engineers, a decision made on bad data, four teams paged for one team's change.
Notes: Walk the tape slowly. The batch job exits 0 — 'success'. Each tool truthfully reports its slice healthy. Root cause found by hand-diffing row counts.

## Slide 5
02 · TARGET STATE
Incident anatomy — target state
≈ 30 minutes
+2 min
Streaming monitor spots the new value and a NULL-rate spike at the topic — one hop from the cause.
+20 min
One incident, not nine alerts: "Deploy a7b2c3 introduced an unmapped value; 6 downstream tables affected." One team paged, cause attached.
+30 min
Certification gate holds the bad batch; consumers keep reading last-certified data. Finance told before the number is used.
The difference: detection before consumption, one page instead of four — bad data never reaches a decision.
Notes: Same incident on the platform. Detection before consumption; one page instead of four; cause and blast radius named; the gate holds the bad batch.

## Slide 6
02 · TARGET STATE
The program at a glance
THE VISION
Every quality, lineage, and pipeline signal joined in one evidence stream — experienced as lineage with health, cause, blast radius, and trust.
THE PLAN
Four foundations, one pilot thread, six months to use case 1 live end-to-end — then use cases onboard on a paved road.
THE ORG
3 mission teams × 10 engineers — Onboarding & Experience, Data Quality, Lineage & Confidence. One foundation each, zero context-switching.
ONE PROGRAM, ONE DEFINITION OF DONE
Every mission converges on one pilot use case; every milestone is a demo on that use case. This is one platform with one definition of done — not three projects sharing a name .
LEADERSHIP'S CONTROL
Kill criteria at month 6: no real saves and no detection improvement → the program stops and the teams redeploy.
Notes: The one-slide version of the whole program. Kill criteria stated up front is what makes the vision credible rather than faith-based.

## Slide 7
02 · TARGET STATE
Four questions, four foundations
THE QUESTION
EXPERIENCED AS
POWERED BY
FIRST LIGHT-UP
What broke?
Lineage canvas with health on it; dataset health chips
Batch, post-write, and streaming DQ federated in one evidence stream
M1–M3
Why?
Causal chain on the incident card; provenance on every edge
E2E lineage joined to evidence and deploy events
M4–M5
Who is affected?
Impact view — reactive blast radius
Lineage plus consumer bindings from the onboarding manifest
M4
How does it stop recurring?
Contracts and certification; impact simulation before a change ships
Contracts & gate; scored graph plus PR-time lineage diff
M6–M7
By month 18: bad data never reaches a Tier-1 consumer unseen; a new use case onboards in ≤ 2 weeks; every lineage edge carries a confidence score.
Notes: Each question maps to a lens of the product, each lens is powered by a foundation, and each has a named moment it first runs on real data.

## Slide 8
02 · STRATEGY
Horizontal foundations, proven vertically
THE PILOT THREAD
payments-svc
→
orders topic
→
enrichment job
→
gold.orders_enr
→
finance report
1
Every milestone is a demo on the pilot thread — "first catch," "blast radius on click," "use case 1 live" — never a percent-complete. A milestone you cannot demo is a status, not a milestone.
2
Every team's definition of done includes landing in the shared evidence stream and naming registry — the one clause that binds three missions to one platform before their first outputs land.
3
Existing batch DQ is improved and federated, never replaced — the first evidence source at M1, the fastest visible win, and it recruits the teams who built it.
Notes: Foundations are horizontal — built once, inherited by every use case. But proven vertically on one pilot thread within six months. Checks shift left over time: at rest first, topic baselines next, service emission last.

## Slide 9
02 · STRATEGY
Alternatives considered
Tool per team
More islands. The failure mode lives in the seams between systems — this is the problem restated as a plan.
Big-bang platform
18 months dark, no kill switch, all demo risk concentrated at the end. Leadership has no checkpoint to steer or stop.
Use-case one-offs
Each use case costs ~6 weeks, forever. Nothing compounds; the estate never gets safer as a whole.
The chosen approach: foundations built once and inherited by every use case — the only alternative where the cost per use case falls with each onboarding.
Notes: Three alternatives were considered and rejected. The foundation approach is the only one where cost per use case falls with each onboarding.

## Slide 10
02 · STRATEGY
Pillar maturity model
L0 doesn't exist
L1 islands, hand-built
L2 connected
L3 runs itself
L4 prevents
PILLAR
TODAY
MONTH 6 GATE
MONTH 12
MONTH 18
Batch data quality
L1
L2 · M1
L3
L4 preventive
Post-write DQ (at rest)
L1
L2 · M2
L3
L4 bound to gate
Streaming DQ (real-time)
L1
L2 · M3
L3
L3 + in-path Tier-1
E2E lineage collection
L1
L2 · M4
L3 scored
L3 + column-level
Data contracts
L0
L1 registry
L3 enforced
L4 gate + in-path
Onboarding experience
L1
L1 runbook
L2 · M8
L3 per type
Data health dashboard
L1
L2 causal
L3 acts
L3 scorecards
No pillar jumps two levels in a phase; L4-everywhere is deliberately not the goal — maturity is matched to asset tier.
Notes: No pillar jumps two levels in a phase. L4-everywhere is deliberately not the goal — maturity is matched to asset tier.

## Slide 11
03 · ROADMAP
Three horizons
NOW · M1–M5
Months 1–6
Foundations live and joined on use case 1 — evidence stream, detection, lineage, dashboard. This is the commitment.
Ends at the go/no-go gate
NEXT · M6–M8
Months 7–9
Prevention and the second use case — contracts, the certification gate's first real block, the paved road proven.
Entered only through the gate
HORIZON · P4
Month 10+
Impact simulation, in-path enforcement, onboarding automation, column-level lineage.
Switched on by trigger, not date
Every milestone names the accountable team, and every milestone is a demo on the pilot thread — never a percent-complete.
Notes: Now is the commitment. Next is entered only through the month-6 gate. Horizon items switch on by trigger, not date.

## Slide 12
03 · ROADMAP — NOW
Milestones M1–M3 — foundations live
M1
Month 1
L&C → DQ, O&E
Evidence stream and naming registry live; existing batch DQ federated; dashboard v0 shows the whole pilot thread in one pane with shared names and source badges.
Proves the join works — and honors existing investment.
M2
Month 2
DQ (async) → O&E
Post-write DQ live: profiling baselines on at-rest datasets; auto-generated freshness and volume checks running out-of-band beside improved batch checks.
Proves the platform learns "normal" without producer effort.
M3
Month 3
DQ (sync) → L&C
Streaming DQ live on the pilot topic — real-time, out-of-band, alert-only. First silent failure caught pre-consumption; saves-ledger entry with counterfactual cost.
Proves detection value is real; ingress detection built once for every future use case.
Notes: M1 honors existing investment — batch DQ federated, not replaced. M2: the platform learns normal without producer effort. M3: first silent failure caught pre-consumption, with a saves-ledger entry and counterfactual cost.

## Slide 13
03 · ROADMAP — NOW
Milestones M4–M5 — the join and the gate
M4
Months 4–5
L&C → O&E
Lineage joined to quality evidence and deploy events; blast-radius view live; every edge provenance-tagged — declared, config-emitted, or runtime-observed.
Proves incidents carry cause and impact, with trust visible per edge.
M5
Month 6
All three teams · O&E orchestrates
Use case 1 live end-to-end on all four foundations. Onboarding runbook v1. Live replay of a real past incident, root-caused in under 30 minutes. Go/no-go gate.
Proves the foundations join on a real case — and beat the war room.
The gate is decided on the scorecard — saves logged, time-to-detect cut — not on architecture progress. Baselines are measured in Phase 0.
Notes: M4 is where incidents start carrying cause and impact. M5 is the gate: use case 1 live on all four foundations, a real past incident replayed and root-caused in under 30 minutes. Go/no-go decided on the scorecard.

## Slide 14
03 · ROADMAP — NEXT
Milestones M6–M8 — prevention and scale
M6
Months 7–8
DQ → domain teams
First producer-accepted contract, auto-drafted from 90 days of observed behavior — a 20-minute review, not a workshop.
Proves prevention becomes possible.
M7
Months 8–9
DQ → L&C
Certification gate's first real block; consumers kept on last-known-good with zero exposure. Confidence scoring live on pilot edges.
Proves bad data can be stopped, not just found.
M8
Month 9
O&E → all
Use case 2 onboarded on the paved road — measurably faster (6 weeks → 2) because it inherits the foundations.
Proves this scales as a product, not a project.
Notes: Post-gate: prevention. First contract auto-drafted from 90 days of observed behavior — a 20-minute review, not a workshop. The gate earns trust in shadow mode before its first real block. M8 proves the product scales.

## Slide 15
03 · ROADMAP — HORIZON
Horizon capabilities, switched on by trigger
Nothing on this list waits for a date — each switches on when its dependency exists.
Impact simulation + PR-time lineage diff
Trigger ← a confidence-scored lineage graph exists
In-path asserts (Tier-1 streams)
Trigger ← an accepted contract plus a recurring violation class
Onboarding automation
Trigger ← the same use-case type onboarded manually twice
Column-level lineage
Trigger ← incidents that demanded a column-level answer
Notes: Nothing on this list waits for a date — each capability switches on when its dependency exists. This is how the horizon stays honest.

## Slide 16
04 · EXECUTION
Three mission teams, thirty engineers
Each team owns one foundation end-to-end — mission, build, run, and its milestones. Nobody is split across projects.
10
Lineage & Confidence
Owns the platform core
10
Data Quality
Owns detection → prevention
10
Onboarding & Experience
Owns adoption & the surface
CONVERGENCE, ENGINEERED
One pilot thread
Evidence stream in every definition of done
Weekly joined demo from week 4
Milestone = cross-team demo
Notes: Each team owns one foundation end-to-end: mission, build, run, milestones. Nobody is split across projects. Convergence is engineered, not hoped for.

## Slide 17
04 · EXECUTION
Mission charters
Lineage & Confidence
Every signal joins under one identity, and every lineage edge is trustworthy — capture → join → score → simulate.
Squads: platform core (3) · lineage collectors (4) · join, provenance & confidence (3)
Done = an edge is in the evidence stream, named in the registry, provenance-tagged.
Data Quality — sync + async
No silent failure reaches a consumer — checks at rest, detection in-stream, then contracts and the gate.
Squads: async / post-write (4) · sync / streaming (4) · contracts & gate (2 → 4)
Done = a check's result lands in the evidence stream under registry names.
Onboarding & Experience
The platform is usable, provable, and cheap to join — the dashboard, the paved road, and the value evidence.
Squads: dashboard & incident experience (5) · paved road (3) · value governance (2)
Done = every view reads only the evidence stream — if it isn't joined, it can't render.
Notes: Read each definition of done — that clause is what makes three teams one platform: everything joins, or it doesn't count.

## Slide 18
04 · EXECUTION
Capacity by phase
TEAM
P0 · WKS 1–4
P1 · M2–3
P2 · M4–6
P3 · M7–9
P4 · M10+
Lineage & Confidence
core 5 · collectors 5
core 3 · collectors 5 · join prep 2
join 6 · confidence 2 · run 2
confidence 4 · UC2 3 · run 3
simulation 5 · column-level 3 · run 2
Data Quality
federation 4 · profiling 3 · stream 3
auto-checks 4 · stream 4 · contracts 2
tuning 4 · shadow gate 3 · generator 3
contracts + gate 6 · run 4
in-path Tier-1 4 · widening 6
Onboarding & Experience
dashboard 5 · manifest 3 · governance 2
dashboard 4 · runbook 2 · UX 2 · scorecard 2
causal view 5 · gate pack 3 · runbook 2
UC2 + template 5 · contracts UX 3 · govern 2
automation 5 · govern 3 · UX 2
At no point does any team run more than three concurrent builds. Contracts stay at two designers until the gate passes; automation is staffed only after two manual onboardings exist.
Notes: Read the columns: at no point does any team run more than three concurrent builds. Contracts stay at two designers until the gate passes; automation is staffed only after two manual onboardings.

## Slide 19
05 · CRITICAL PATH
Critical path and dependencies
DEPENDENCY
ASK
NEEDED BY
IF IT SLIPS — PLAN B
Data platform / governance THE critical ask
Agree one naming registry is the authority — pilot's ~10 assets first
P0
Every join fails silently later — the #1 program risk. Scoped small to be decidable fast.
Streaming platform
Read-only monitor credentials, topic catalog, schema registry read
P0
Detection starts at tables; monitor runs in our account as an ordinary consumer.
Central DQ tooling
Read access to check results
M1
Scheduled export — same data, slightly staler.
Platform engineering (CI/CD)
Deploy events with commit + timestamp, pilot pipelines only
M4
Incidents name the system, not the deploy; infer from logs.
Cross-team interlocks
Ingest contract (wk 4) · manifest schema (wk 3) · check-result shape (wk 4)
P0
Versioned stubs and raw-evidence rendering keep every team unblocked.
Dependency health is a monthly scorecard item with sponsor escalation — a slip is surfaced, never absorbed silently.
Notes: One critical ask: the naming registry as authority, scoped to the pilot's ~10 assets to be decidable fast. Everything else is read-only. Dependency health is a monthly scorecard item with sponsor escalation.

## Slide 20
05 · GOVERNANCE
Governance mechanisms
Saves ledger
Opens at M1. Every catch logged with its counterfactual: who would have consumed the bad data, what the last comparable incident cost.
Monthly scorecard
Fixed cadence: time-to-detect, time-to-root-cause, teams paged per incident, saves banked, foundations joined (0→4), dependency health.
Demo cadence
Reviews are live replays on the pilot thread — the war room, then the causal chain. Milestones are demos; there is no "percent complete."
Sponsor-owned KPI
The pilot thread is chosen so its health maps to one executive sponsor's own metric — one leader personally invested in the M5 replay.
Notes: Fixed cadence so silence is never read as stall. Reviews are live replays on the pilot thread, not status decks. The pilot maps to one executive sponsor's own metric.

## Slide 21
05 · GOVERNANCE — STATED UP FRONT
Kill criteria at month 6
If by the M5 checkpoint the pilot thread has not logged real saves and cut time-to-detect below the agreed threshold — with all four foundations live and joined on use case 1 — the program stops and thirty engineers redeploy to their domains.
Offering leadership the kill switch is what makes the vision credible rather than faith-based. Baselines are measured in Phase 0; the gate is decided on the scorecard, not on architecture progress.
Notes: Offering leadership the kill switch is what makes the vision credible rather than faith-based. Baselines measured in Phase 0; the gate decided on the scorecard, not architecture progress.

## Slide 22
06 · OUTCOMES
Outcomes at months 6, 11, and 18
Month 6
All four foundations live and joined on use case 1 — lineage with health, cause on the incident card, reactive blast radius. Go/no-go gate.
Month 11
Full platform live — enforcement and gating on, edges confidence-scored, multiple use cases onboarded on the paved road.
Month 18
Critical use cases operating; impact simulation and PR-time diff on Tier-1; column-level depth where incidents demanded it; expansion priced from measured cost per use case.
DELIBERATELY NEVER ON ANY TEAM'S LIST
"Map everything" lineage crawls · estate-wide enforcement mandates · L4 everywhere · blocking on anomaly scores · automation before two manual samples.
Three missions, one evidence stream, one pilot thread, one scorecard — one platform, not three projects.
Notes: Close on the outcome ladder — and on what the program refuses to do. What a program refuses to do is half of its vision. One platform, not three projects.